# INTRODUCTION

## PRESENT SITUATION:

Problem Statement derived from the EWR.

## PROPOSED SOLUTION:

Proposed Solution presented in this Job Pack.

# SCOPE OF WORK

- BUSINESS PARTNER (BP) shall strictly follow all relevant TCO Safety Instructions in the progress of works, all of which are readily obtainable from the TCO Intranet.

- BUSINESS PARTNER (BP) shall follow all Quality Management (QM) requirements designated in the Quality Control package.

## PRELIMINARY SITE WORK:

    - Prior to the start of the mechanical activities, perform wall thickness testing at TPxx-yyy/000 and TPxx-yyy/999 to confirm that wall thickness is adequate for welding. Results shall be reviewed and approved by the Fixed Equipment Reliability (FER) Unit Inspector.

NOTE:  Perform the wall thickness test by marking out and recording a matrix as directed by the TCO FER Unit Inspector.

    - Prior to commencing any fabrication works verify dimensions marked with asterisk (*), pipe routing and field weld locations on site.

NOTE: When allocating FW & FFW locations for machinery nozzle connections [OR] fixed equipment nozzle connections [OR] PSV inlet/outlet connections, consider the possibility of final piping adjustment after nozzle alignment completion.

[Use when insufficient data available for DTEC to verify Pressure Vessel internal dimensions or configuration prior to AFC issue]

NOTE:  Invite Responsible Engineer to verify dimensions / internal configuration / XXX on site, once vessel is isolated and full access is provided.

    - Prior to excavation works, for installation of pipe support foundation(s) in unpaved areas, perform surveying work for the presence of underground utilities. Arrange this with the TCO Lead Field Surveyor, phone 4931.

    - Perform excavation works and install concrete foundation of new unpaved area pipe support(s) as per isometric drawing(s) 00-YYYY-L-ZZZZ and the attached drawing from Tengiz Engineering Specification (TES) L-ST-6075.

    - [Add this step when replacing existing equipment (valve, pressure vessel etc) with new equipment and the weight of new equipment is much heavier than existing one] Consider the weight of the new equipment indicated on drawing XXXX during developing execution steps and lifting plan.

NOTE: DTEC completed required engineering studies of existing/new piping, foundation & supports and confirmed new equipment weight is within allowable loads.

## SHOP WORK:

    - Withdraw materials required for this Job Pack from TCO Warehouse according to Material Request(s).

    - Perform Positive Material Identification (PMI) as per TCO RE QM SWP-20 Procedure on all corrosion resistant alloy (CRA) materials and weld consumables.

    - Prefabricate pipe spools and pipe supports, as per isometric drawing(s) 00-YYYY-L-ZZZZ. Use TCO-approved Welding Procedure Specification(s) (WPSs) indicated on isometric drawing(s).  BP shall comply with TCO Guideline 16-0015-MI for socket-welded joints.

    - Perform post weld heat treatment (PWHT) as specified by WPS and in compliance with TES PIM-SU-2505/W-ST-2011 /2016 / 2026 / 2028.

    - Perform non-destructive examination (NDE) and hardness testing of shop welds, as specified on isometric drawing(s) 00-YYYY-L-ZZZZ.

NOTE: Perform NDE and hardness testing only after PWHT!

NOTE: BP must check with MaxTrax admin on NDE requirements prior to commence welding works.

    - Perform shop hydrostatic testing of flanged spools as specified on isometric drawing(s) 00-YYYY-L-ZZZZ in accordance with TES PIM-SU-3541-TCO [OR] Perform shop hydrostatic testing of ASME B31.4 / B31.8 pipeline components in accordance with TCO Procedure X-000-L-PRO-0001 as per isometric drawing(s) 00-YYYY-L-ZZZZ – 4-hour duration.

NOTE: Test water used for 300-series stainless steel piping shall be water with chloride content of less than 50 ppm. Perform Water Sampling and Analysis per TES PIM-SU-3541-TCO Section 5.

    - Abrasive blast and coat new piping spools and supports, as specified on isometric drawing 00-YYYY-L-ZZZZ in accordance with TES COM-SU-5191-TCO.

NOTE: Mask-off field-weld joints and flange faces prior to coating.

  - SITE WORK:

    - Perform relevant job safety assessments (PPHA & JSA) and obtain required Permits-to-Work (PTWs).

    - Demarcate work area as necessary and erect scaffolding for access.

NOTE: TCO Operations shall isolate, depressurize, drain and ready for Hot Work, Equipment and Piping associated with this Project, if and as applicable, and shall hand it over to BUSINESS PARTNER (BP); fully accessible, safe and Locked-Out-Tagged-Out (LOTO) as scheduled and agreed between TCO Operations and BP.

    - [Only when dismantling piping with existing spring support and reusing spring support] A spring stopping pin must be installed before pipe dismantling. Note that the pin must be removed on the same condition as it was installed. If pipe was full at installation of pin, new pipe must be filled prior to pin removal. Spring level / indicator must be marked on hot and cold conditions.

    - Remove all cladding and insulation to the extent required.

    - [Only when dismantling piping with existing spring support and reusing spring support] Check list MCL005A-1 (Spring Support Verification for Maintenance) shall be completed and signed by responsible parties.

    - [Only when working on piping connected to machinery] Invite Machinery Maintenance team to install dial gauges prior to existing piping dismantle to record “Zero” position of the compressor/pump.

NOTE: Gauges stay on until all work is complete. Last step is a left record of gauges and gauge removal prior to buttoning up and restart.

    - Arrange with Tengiz Turnaround Team (TTT) I&E Coordinator [OR]  Zone Maintenance to isolate, LOTO and remove electric trace heating and instruments from associated piping per I&E Job Pack YY-NNNN.1 [OR] Carefully remove for reinstatement (or Demolish) hot water / steam tracing where necessary.

NOTE: BP to match mark, call a unit operator, show the mark and record location prior to cutting and removal to aid in reinstatement of heat tracing.

    - Apply and sign special tape, which determines the place of cutting the pipe, according to SP-26 at TP-XXX. Follow all the steps of SP-26.

    - Cold Cut, unbolt and remove existing piping and pipe supports shown on “Destruct Detail” of isometric drawing(s) 00-YYYY-L-ZZZZ. Make good any remaining foundations and/or metal structures and perform coating repairs per TES COM-SU-5191-TCO. [OR] Remove the redundant plinths and/or metal structures, supports.

    - Perform hydrogen bake-out in the weld zone of each tie-in points as shown on isometric drawing(s) 00-YYYY-L-ZZZZ following requirements in TES PIM-SU-2505.

    - Bevel cut ends of existing piping at the tie-in point(s) TPxx-yyy/000 for field welding as shown on isometric drawing(s) 00-YYYY-L-ZZZZ.

    - Inspect the prepared weld bevel ends 100% VT and 100 % MT/PT for defects.

NOTE: Perform inspection of weld bevels and nipo-flange landings PRIOR to welding.

    - Perform PMI at field joints as per TCO RE QM SWP 20 Procedure on alloy materials listed in SWP-20 Appendix 20-1.

    - Install piping as specified on isometric drawing 00-YYYY-L-ZZZZ. For field welds use TCO-approved WPSs indicated on isometric drawing(s).  BP shall comply with TCO Guideline 16-0015-MI for socket-welded joints.  BP shall comply with additional weld controls denoted in Closure Weld Package(s) CW-00-0YYY/00X.

NOTE: Do NOT drill the header or cut out nipo-flange coupons prior to hydro-testing branch connections.

NOTE: [For machinery installation projects only] Verify the piping alignment with respect to machinery suction/discharge nozzle before the field welding. Flange alignment shall be parallel to pump nozzle with ability to insert/remove bolting without any binding.  Flange-face gaps shall only accommodate Gasket including Spec Blind as applicable. API 686 shall be followed for alignment requirements.

    - Install civil structural support as per isometric drawing 00-YYYY-L-ZZZZ and attached Standard Support drawing.

    - Perform PWHT of field joints as specified by WPS and in compliance with TES PIM-SU-2505/W-ST-2011 /2016 / 2026 / 2028, PCR-PU-6239 and W-ST-2006.

    - Perform NDE and hardness testing of field welds, as specified on isometric drawing(s) 00-YYYY-L-ZZZZ.  BP  shall comply with specified NDE requirements denoted in closure weld package(s) CW-00-0YYY/00X.

NOTE: Perform NDE and Hardness Testing only after PWHT!

NOTE: BP must check with MaxTrax admin on NDE requirements prior to commence welding works.

    - Perform field hydrostatic testing of new piping as specified on isometric drawing(s) 00-YYYY-L-ZZZZ in accordance with TES PIM-SU-3541-TCO [OR] Perform ASME B31.4 / B31.8 pipeline hydrostatic testing in accordance with TCO Procedure X-000-L-PRO-0001 as per isometric drawing(s) 00-YYYY-L-ZZZZ – 4-hour duration.

NOTE: Test water used for 300-series stainless steel piping shall be water with chloride content less than 50 ppm.  Perform Water Sampling and Analysis per TES PIM-SU-3541-TCO Section 5.

    - Perform surface preparation and touch up field welds and any other coating damages in accordance with TES COM-SU-4743-TCO and coating system(s) per TES COM-SU-5191-TCO specified on drawings.

    - [Add this step only for SS piping which has heat tracing on it. The reason is to avoid the risk of chloride cracking of seam welds from heating it by trace heating to certain temperature in presence of chlorides.] Apply Aerogel (Pyrogel) insulation on seam welds prior heat tracing installation in accordance with P-ST-6199.

    - Arrange with TTT I&E Coordinator [OR]  Zone Maintenance to reinstate / install related electric trace heating and instruments, as per I&E Job Pack YY-NNNN.1. [OR] Reinstate hot water / steam tracing and conduct NDE as well as service testing of each separate loop.

    - All QM piping passport documentation (A-category Checklists) to be verified and signed by TCO-approved QM Inspector prior to PSSR, but not later than 24 hours after mechanical scope completion.

    - Advise xxxxx yyyyy/ zzzzz mmmm, DTEC KTL Plant Support / DTEC T/A / SGP/SGI, / FUPO Engineer at ext. 0000 about work completion and invite all necessary people to PSSR.

NOTE: [For machinery installation projects only] Arrange with RE Integrated Machinery Inspection (IMI) group (x3969/x7375) for inspection of suction/discharge flange alignment prior to torqueing of bolts to rotating equipment nozzles.

[AND / OR]

NOTE: Fixed Equipment nozzle [OR] Machinery connections [OR] PSV connections [OR] Swing Elbow connections [OR other strain sensitive equipment subject of the JP] flange alignment to be witnessed and accepted stress-free by TCO Designs & Technical Engineering Center (DTEC) and RE QM [for Routine] [OR] Bolting Team [for TA], prior to PSSR

    - Job Pack Coordinator shall submit the completed PIC check-list to Operations department after being signed by Quality Management group. (Form is provided by QM Dept.).

    - Conduct PSSR and close out A-category punch points.

    - Following PSSR reinstate / install insulation and cladding, as per TES IRM-SU-1381-TCO and as specified on isometric drawing 00-YYYY-L-ZZZZ.

    - Close out all B-category punch points and remove associated scaffolding.

    - Clean up the work area and demobilize from site.

  - AFTER COMPLETION OF WORK

    - Perform service test.

    - Final as-built package (including B-category Checklist) shall be submitted to TCO QM group within 2 weeks after completion of the whole scope of works.

    - Return excess material to TCO Warehouse.

# ATTACHMENTS:  [Generally in the order shown below, see also sect 4. of READ ME  document for JP Template]

| ### DOCUMENT TYPE | ### DOCUMENT TITLE | ### DOCUMENT NUMBER # | ### REV. |
| --- | --- | --- | --- |
| # EWR | # EWR or IWR | # EWR/IWR YY-0NNN | # N/A |
| # TCO Plot Plan | # SGP/SGI/Unit plot plan | # 60-0000-L-SHK-XXXX | # A |
| # P&ID | # Project Piping & Instrument Diagram | # (varies) | # (varies) |
| # Drawing | # Isometric drawing | # 00-0XXX-L-XXXX | # A |
| # Plans | # Repair Plans / PWHT Plans / NDE Special Requirements / ITPs | # (varies) | # (varies) |
| # Project MR | # Material requisition for piping | # YY-0NNN-001 | # N/A |
|  | # Material requisition for supports | # YY-0NNN-002 | # N/A |
| # TCO Standard | # Specification for Pipe Supports | # L-ST-60XX | # 0 |
| # Equipment Ref Drawings | # Main Equipment General Arrangement | # YY-0000-X-XXX | # latest |
| # In-Line Equipment Ref Drawing | # Vendor Equipment General Arrangement & Details | # Vendor Drg/Doc # | # (varies) |
| # Line List | # Unit XXX Unit Wide Line List | # 00-YYYY-L-PLL-000Z |  |
| # QM Index | # Quality Management Documents | # (Pending) | # latest |

# REFERENCED TCO SPECIFICATIONS:

A-ST-2008 			Basic Engineering Data

PIM-SU-2505-TCO 		Piping Fabrication

SI-105				Permit to Work and Hazard Analysis

SI-121 			Hot Tapping

PIM-SU-5209-TCO		Flange Gaskets and Bolting

PIM-SU-3541-TCO 		Hydro testing of onshore piping system

X-000-L-PRO-0001              Hydrostatic Testing of piping systems

X-000-L-PRO-0002              Procedure for the control of closure welds

WEM-SU-5246-TCO	Use of Non-Pressure-Tested Closure Welds

PIM-SU-2411-TCO 		Descaling and Cleaning Steel Piping

COM-SU-4743-TCO 	External Coatings

COM-PU-4738-TCO	Internal Coatings

COM-SU-5014-TCO	Internal Coatings for Vessels in Wet H2S Service

COM-SU-5191-TCO            Coating systems

CIV-SU-398-TCO		Fabrication of Structural and Miscellaneous Steel

CIV-SU-581-TCO		Site Preparation, Excavation and Backfill

CIV-SU-850-TCO		Plain and Reinforced Concrete

CIV-SU-985-TCO		Cementitious Grout

W-ST-2004 			Materials in Wet H2S Service

W-ST-2011 			Welding, PWHT and NDT of Pipelines

W-ST-2016 			Welding of HP Gas Injection System Pipelines and Pipework

W-ST-2026			Welding of Wellhead Flow Loop Pipework

W-ST-2028 			Welding of Heavy Wall ASTM A 182 Grade F22 Piping

W-ST-2006 			Welding, NDE and PWHT of Pressurized Equipment

IRM-SU-1381-TCO 		Thermal Insulation for Hot Lines, Vessels and Exchangers

IRM-SU-2634-TCO		Thermal Insulation for Cold Lines, Vessels, and Exchangers

LokRing® Vendor LP-105	Installation Procedure for LOKRING Fittings

TCO-REQM-SWP-20	Positive Material Identification (PMI)

CPM-PU-5074-TCO		Positive Material Identification Program for Source PMI.

MAC-SU-5100-TCO		Installation and Precommissioning of New & Reapplied Machinery Exception to API 686

SP-26				Line cutting

PCR-PU-6239-TCO             Field and Local Post Weld Heat Treating